## Sheet1
BLACKPOOL BRIDGES PROJECT - APPENDIX D
RISK REGISTER Version 1 - 02/01/15
Risk Identification | [7 empty] | Qualitative Risk Assessment | [8 empty] | Risk Response Plan |  | Monitoring and Control
| Status | Risk Category | Risk Event | Cause | Effect | Threat or Opportunity | Primary Objective | Probability | Impact | Risk Matrix | [6 empty] | Response Strategy | Response Actions | Responsible Entity | Interval or Milestone Check | Status: Date and Review Comments
1 | Active | External | Project not fully funded | Budget Constraints- allocation in doubt or subject to change | Project delayed | Threat | Time | Low | Very High | Probability | VH | [5 empty] | Mitigate through HAMP, Lifecycle Planning and Communications Plan | Project may be divided into 2 or 3 phases | Project Sponsor | Monthly | 2015-02-02
H
M
[11 empty] | L |  |  |  |  | X
VL
[12 empty] | VL | L | M | H | VH
Impact
2 | Becomes active 2017 | External | Major disruption to highway network if project fails with consequential effects on business, growth and tourism in the area | Budget Constraints- allocation in doubt or subject to change | No inward investment | Threat | Time | Low | Very High | Probability | VH | [5 empty] | Mitigate through HAMP, Lifecycle Planning and Communications Plan | Project may be divided into 2 or 3 phases | Project Sponsor | Monthly | 2015-02-02
H
M
[11 empty] | L |  |  |  |  | X
VL
[12 empty] | VL | L | M | H | VH
Impact
3 | Long-term | External | Major disruption to rail routes in and out of Blackpool due to failing bridges. | Budget Constraints- allocation in doubt or subject to change | No inward investment | Threat | Time | Low | Very High | Probability | VH | [5 empty] | Mitigate through HAMP, Lifecycle Planning and Communications Plan | Project may be divided into 2 or 3 phases | Project Sponsor | Monthly | 2015-02-02
H
M
[11 empty] | L |  |  |  |  | X
VL
[12 empty] | VL | L | M | H | VH
Impact
4 | Active | External | Damage and disruption to passing trains due to loose and spalling concrete. | Budget Constraints- allocation in doubt or subject to change | Death or serious injury. Reputation risk. | Threat | Health & Safety | Low | Very High | Probability | VH | [5 empty] | Mitigate through increased frequency of trackside inspections | Increase frequency of inspections | Network Rail | Monthly | 2015-02-02
H
M
[11 empty] | L |  |  |  |  | X
VL
[12 empty] | VL | L | M | H | VH
Impact
5 | Active | External | Failure to undertake work to Plymouth Road Railway Bridge in advance of Network Rail line electrification | Budget Constraints- allocation in doubt or subject to change | Project cost increased significantly | Threat | Time and cost | Medium | High | Probability | VH | [5 empty] | Mitigate through budget re-profiling budget | Early liaison with Network Rail ongoing | Project Manager | Monthly | 2015-02-02
H
[11 empty] | M |  |  |  | X
L
VL
[12 empty] | VL | L | M | H | VH
Impact
6 | Active | External | Statutory undertaker’s plant and equipment within the bridge deck requiring diversion or temporary support. | Unforeseen event | Project delayed and additional cost | Threat | Time and cost | Low | High | Probability | VH | [5 empty] | Mitigate through trial holes, ground radar and SU liaison | Advanced trial holes and investigation ongoing | Project Manager | Monthly | 2015-02-02
H
M
[11 empty] | L |  |  |  | X
VL
[12 empty] | VL | L | M | H | VH
Impact
7 | Active | Internal | Seasonal traffic management restrictions on local road network. | Programming constraints | Project delayed | Threat | Time | Low | Medium | Probability | VH | [5 empty] | Mitigate through off-season working, overnight closures and liaison with NR | Early liaison with BBC TMA Officer ongoing | Project Manager | Monthly | 2015-02-02
H
M
[11 empty] | L |  |  | x
VL
[12 empty] | VL | L | M | H | VH
Impact
8 | Active | External | Lack of availability of track possessions leading to delays | Programming constraints | Project delayed | Threat | Time and cost | Medium | High | Probability | VH | [5 empty] | Mitigate through early planning and liaison with NR | Early liaison with Network Rail ongoing | Project Manager | Monthly | 2015-02-02
H
[11 empty] | M |  |  |  | x
L
VL
[12 empty] | VL | L | M | H | VH
Impact
9 | Active | External | Third party resource limitations (Network Rail and Statutory Undertakers) | Programming constraints | Project delayed | Threat | Time and cost | Low | High | Probability | VH | [5 empty] | Mitigate through early planning and liaison with NR and SU | Early liaison with Network Rail and Statutory Undertakers ongoing | Project Manager | Monthly | 2015-02-02
H
M
[11 empty] | L |  |  |  | x
VL
[12 empty] | VL | L | M | H | VH
Impact
10 | Active | External | Third party procedural requirements (Network Rail). | Programming constraints | Project delayed | Threat | Time and cost | Medium | High | Probability | VH | [5 empty] | Mitigate through early planning and liaison with NR | Early liaison with Network Rail ongoing | Project Manager | Monthly | 2015-02-02
H
[11 empty] | M |  |  |  | x
L
VL
[12 empty] | VL | L | M | H | VH
Impact