## Sheet1
Headings and page numbers relative to previous version of the ASR document
Number | Chapter | Subheading/ Table/ Figure | Page | Comment | Response
1 | 1 - Introduction | Fig 1.1 | 3 | A wider study area should be shown to include Roman Road, Brandy House Brow and Old Bank Ln, as these parallel routes will be significantly impacted. Can the sections to be widened, and the junctions being modified or added, be shown. | This figure is intended to simply highlight the location of links + junctions where a specific intervention is proposed. Figures provided in later sections highlight the wider study area/ modelled extent.
2 | 2 - Challenges and Issues | 2.3 - Options considered | 6 | Can an option assessment history be provided. What non-highway options were considered? Did you consider whether PT and active mode elements could be integrated into the scheme? | Options Assessment Summary Technical note will be provided as well as an EAST assessment to provide a short summary of the options considered across the corridor and at specific locations This will include alternative sustainable and active travel modes
3 | 2 - Challenges and Issues | 2.3 - Options considered | 6 | What alternative highway options existed, and why was the preferred option chosen? What is the next-best alternative if the preferred option cannot be delivered? | Options Assessment Summary Technical note will be provided as well as an EAST assessment to provide a short summary of the options considered across the corridor and at specific locations
4 | 3 - Transport Modelling | Fig 3.1 | 11 | Note this is significantly broader than the study area shown above. Can the coverage of the model be shown in this figure? | Figure updated to highlight the extent of the likely impact area and reflective of baseline VISSIM modelling
5 | 3 - Transport Modelling | 3.3 - Traffic Data Collection and Analysis | 13 | Normally would expect 2 weeks of data for WebTAG compliant model validation. Is this available? If MCCs are only 1-day, what evidence is there that traffic conditions on that day were representative of typical conditions? | MCC Data across the study area has been taken from a number different sources, including historical ATCs and MCCs undertaken in support of TAs for local planning applications. where avalible these will inform vehicle inputs/ traffic flows through the baseline VISSIM network. Model validation and performance relative to baseline conditions will be undertaken against TomTom travel time data, averaged across a month long period along key study area routes. further details will be provided in the baseline LMVR
6 | 3 - Transport Modelling | Tab 3.1 | 14 | A count on Roman Road would be useful | As is now detailed in the updated ASR, a classified turning count from march 2019 for the Roman Road / Blackamoor Road junction has been aquired and used to inform baseline traffic conditons along Roman Road
7 | 3 - Transport Modelling | Tab 3.1 | 14 | This is not a neutral month – can it be demonstrated that this is adequately representative of typical conditions? | Table 3.1 has been updated from the previous version of the ASR and contains updated traffic count data from more recent traffic counts
8 | 3 - Transport Modelling | 3.6 - Proportionality of modelling approach | 16 | Could you please provide a map showing the existing model area and the proposed extension. | Map of VISSIM model extent now provided in ASR.
9 | 3 - Transport Modelling | 3.6 - Proportionality of modelling approach | 16 | As mentioned above, we believe the study area will need to include Roman Road and Brandy House Brow as a parallel route, and therefore so would the VISSIM model. | See response below.
10 | 3 - Transport Modelling | 3.6 - Proportionality of modelling approach | 16 | We note that Google Maps’ suggested routes between the Blackamoor Road distribution centre and central Blackburn shows no identifiable difference in Journey Time or Distance between Roman Rd or the A6077. Aspects of the scheme will improve JTs on both of these routes Similarly we note that route choice between Stopes Brow in Lower Darwen and the Hospital, and the residential areas off Roman Rd and the M65 indicates near equal preference for the two parallel routes. As such, we would expect route choice in this area to be quite sensitive and the potential for changes in route choice in response to the upgrades will need to be considered in the model to fully determine the level of benefits. | Journeys between Blackburn town centre and the Blackamoor distribution centre are unlikely to impact significantly on the peak periods due to shift patterns. Any HGV movements will be on set routes, likely following motorways and primary routes so any route choice variability associated with journeys between these two locations are likely to be negligible. Given the extent of modelling already undertaken, project timescales, the scale of the overall scheme and its intendend impacts, the current approach and modelled is deemed sufficient to capture the intended scheme impacts. The modelling approach is consistent with other growth deal schemes across Lancashire of a similar nature and scale. The example of route choice presented is not realistic as this assumes a choice of access to the hospital. In reality visitors would not have a choice of access. The access close to the Old Bank Lane junction (KFC) serves
11 | 3 - Transport Modelling | 3.8 Modelling and Appraisal Assumptions | 17 | This section is mainly discussing development traffic, not background growth. How will baseline traffic growth be determined? Presume based on TEMPRO/NTEM, what factors will be used? | Text added as in section 3.8.2 to provide details of TEMPro/ NTEM growth factors applied.
12 | 3 - Transport Modelling | 3.8 Modelling and Appraisal Assumptions | 17 | This is “practical capacity” – normally defined as the point beyond which delay starts to increase non-linearly with increased demand. This is not an actual capacity constraint and the network will be capable of accommodating more capacity. | Point noted - text ammended in the ASR to reflect comments
13 | 3 - Transport Modelling | 3.8 Modelling and Appraisal Assumptions | 17 | Many parts of the UK transport network continue to operate and see traffic growth despite already exceeding local “practical capacity”, and many planning authorities continue to grant permission to developments where the local network exceeds this threshold. Indeed, as discussed on the NE Blackburn scheme, this is already the case in the local area where developments have been allowed in proximity to key junctions with peak hour capacity ratios in excess of 1.00. | List of committed and potential future developments has been updated, reflectibe of comments received and updated information provided by BwDBC. Many of the developments in the list of committed developments provided in the updated ASR have planning permission and are not considered dependent on the current scheme. Planning permission has been granted for these despite known capacity and congestion issues on the local highway network. A seperate dependent development list has also now been produced to identifiy potential future development sites likely to be dependent on the proposed scheme. Justification for dependency also provided.
14 | 3 - Transport Modelling | 3.8 Modelling and Appraisal Assumptions | 17 | As such, we would expect there to be continued background growth in traffic levels in future years. | Background growth forecasting in line with TEMPro growth factors applied to the network under future forecast conditions. All forecasts controlled to NTEM in line with TAG guidelines
15 | 3 - Transport Modelling | 3.8 Modelling and Appraisal Assumptions | 17 | Trip totals in the Baseline and Core Scenario should include consideration of the impact of “peak spreading” and whether a) peak spreading will occur in the Baseline and b) whether the improvements will result in less peak spreading in the Do Something and a resulting sharper peak with higher peak-hour trip volumes. This could be in the form of a sensitivity test. | Any potential for peak spreading is likely to be minimal and is expected to fall within the extents of low growth and high growth sensitivity tests being undertaken around the core scenario.
16 | 3 - Transport Modelling | 3.9 Scenario Specification | 17 | Conflicts with Section 4.2.6 and 3.9.4 – if these developments are dependent, then they should not be included in the Baseline or Core Scenario demand. | Justification for dependent development, proposed scenario specification and proposed apprasial methodology surrounding dependent development has been updated to refelct comments provided on the ASR as well as up to date proposed development information provided by BwDBC
17 | 3 - Transport Modelling | 3.9 Scenario Specification | 17 | The Baseline scenario should match the scenario termed “Scenario P” in WebTAG A2.2, i.e. with demand from background growth and deadweight land use changes. | Justification for dependent development, proposed scenario specification and proposed apprasial methodology surrounding dependent development has been updated to refelct comments provided on the ASR as well as up to date proposed development information provided by BwDBC
18 | 3 - Transport Modelling | 3.9 Scenario Specification | 18 | This section contradicts 3.9.4 below, Recommend adopting the naming convention used in WebTAG A2.2 for clarity. | Naming convention of future forecast scenarios now defined in ASR in line with tag A2.2
19 | 3 - Transport Modelling | 3.9 Scenario Specification | 18 | This scenario should match WebTAG A2.2’s “Scenario S” – i.e. with the same land use as the Baseline (background + deadweight) and with the scheme. | Naming convention of future forecast scenarios now defined in ASR in line with tag A2.2
20 | 3 - Transport Modelling | 3.9 Scenario Specification | 18 | The scenario described as a “sensitivity test – dependent development” should match “Scenario R” – with the scheme and with all land use change associated with the dependent development | Naming convention of future forecast scenarios now defined in ASR in line with tag A2.2
21 | 3 - Transport Modelling | Tab 3.3 - Housing Developments | 19 | How many units are outstanding? | Tables reviewed and broken down into committed and potential future development based on updated info about development sites aquired from BwDBC since writing the origional ASR
22 | 3 - Transport Modelling | 3.9 Scenario Specification | 21 | Please ensure consistency with approach adopted in 4.2.6 – this should match Scenario R from WebTAG A2.2 | Justification for dependent development, proposed scenario specification and proposed apprasial methodology surrounding dependent development has been updated to refelct comments provided on the ASR as well as up to date proposed development information provided by BwDBC
23 | 3 - Transport Modelling | 3.9 Scenario Specification | 21 | This is not a conservative approach. A conservative approach is to assume less dependency | Dependent development methodology and justification sections have been updated to provide a more clearly defined list of committed and potential future development, with specific developments considered dependent
24 | 4 - Economic Appraisal | 4.2 Proposed Methodology | 23 | Please can a table of key assumptions be provided. This should include things such as opening year, final forecast year, appraisal period, TAG databook version, economics price base (i.e. 2010 market prices and values discounted to 2010) etc. | Summary Table now included now as Table 4.1 on page 26 covering key apprasial assumptions
25 | 4 - Economic Appraisal | 4.2 Proposed Methodology | 24 | To ensure the business case is compliant with the LEP assurance framework, a GVA assessment will be needed. We would expect this to be included in this section. | Text updated in ASR to reflect this approach in section 4.2.6, presenting GVA methodology and calculation in the VfM statement
26 | 4 - Economic Appraisal | 4.2 Proposed Methodology | 24 | Please ensure sufficient detail is provided that we can confirm the approach and outputs will be consistent with the LEP assurance framework. | As above, text updated in ASR to reflect this approach in section 4.2.6
27 | 4 - Economic Appraisal | 4.2 Proposed Methodology | 24 | We expect that the basis for the GVA calculations will be the same development being unlocked as outlined in A4.2.6. | As above, text updated in ASR to reflect this approach in section 4.2.6
28 | 4 - Economic Appraisal | 4.2 Proposed Methodology | 24 | GVA and dependent development will overlap and contain some double-counting of benefits. This needs to be recognised both in the business case but is not an obstacle. GVA should not be included in calculation of BCRs, so recognition of this overlap will be sufficient to allow both to be considered qualitatively in the VfM statement. | Text in ASR updated to reflect this approach in section 4.2.6, presenting both GVA and calculation of dependent development impacts on BCR seperately.
29 | 4 - Economic Appraisal | 4.2 Proposed Methodology | 24 | No local regeneration areas? | Any regeneration benefit will be captured in assessment of GVA/ dependent development calculations as defined in the updated ASR
30 | 4 - Economic Appraisal | 4.2 Proposed Methodology | 24 | In line with WebTAG A2.1 guidance, we would expect the impact of dependent development (both the Land Value Uplift and the external transport impacts) to be subjected to sensitivity testing rather than included in the calculation of initial/adjusted BCRs. | Methodology in ASR updated to set out core scenario, which excluded land value uplift/ extarnal transport impacts from initial BCR. Dependent development subject to alternative scenario/ BCR.
31 | 4 - Economic Appraisal | 4.2 Proposed Methodology | 24 | We would recommend using the sensitivity testing to identify “switching values” for what proportion of LVU needs to be included in the PVB to lead to an increase in VfM category. This will be sufficient to inform a qualitative judgement on the Value for Money assessment. | Steps will be taken to ensure GVA calculation estimates draw from same sites as those set out in the ASR Text in ASR updated to reflect this approach, presenting both GVA and calculation of depndent development impacts on BCR seperately.
32 | 4 - Economic Appraisal | 4.2 Proposed Methodology | 24 | The evidence in section 3.8.2 isn’t sufficient. You will need a dependency test or planning/feasibility justification to demonstrate why a smaller, privately funded intervention couldn’t allow any of these developments to be built. This could be only building part of the scheme at a later date with private money or LA borrowing to be recouped from developer S106, or smaller local junction improvements, which could allow some nearby sites to be built. There needs to be a trio of planning, transport and feasibility arguments to justify the dependency. | Further evidence has been added to section defining existing conditions and network capacity across the study area to demostrate existing capacity constraints (now Section 3.9) List of committed developments has been provided to show developments with planning permission and not dependent on the scheme. Dependent development list has been updated to reflect comments on ASR and updated information provided by BwDBC. This also provides further details of justification around planning, transport and feasibility arguments
33 | 4 - Economic Appraisal | 4.2 Proposed Methodology | 25 | Planning gain is now normally termed “Land Value Uplift”, can we change terminology throughout. Refer to both WebTAG A2.2 and MHCLG Appraisal Guide. | Terminology changed to land value uplift throughout ASR
34 | 4 - Economic Appraisal | 4.2 Proposed Methodology | 25 | The approach taken to this and GVA should be consistent – you need to claim the same sites, dependencies, acceleration, deadweight and displacement etc. The two can and probably should be combined/pull from the same source, but remember that GVA and LVU are different but some double-counting is likely inherent. | Text in ASR updated to reflect this approach, presenting both GVA and calculation of depndent development impacts on BCR seperately.
35 | 4 - Economic Appraisal | Tab 4.1 - Potential Dep Dev Sites | 26 | Can this table be made to include site area, number of houses, employment floorspace and number of jobs as requested in original email | Dependent development table updated and now contains housing numbers/ economic floor space etc
36 | 4 - Economic Appraisal | Tab 4.1 - Potential Dep Dev Sites | 26 | This site is listed as already under construction in table 3.3 – cannot have dependency unless there is a planning link – why is this proportion of the site dependent? (A S106 condition?) | Dependent development table updated - this development now considered committed, with planning permission and not dependent on the scheme
37 | 4 - Economic Appraisal | Tab 4.1 - Potential Dep Dev Sites | 26 | This site is listed as in pre-construction in table 3.3 – is there already planning permission? If so, what is the planning link to the scheme? If not, what evidence is there that permission would not be granted if the scheme were rejected? Why is the stated proportion of the site dependent? | Dependent development table updated - this development now considered committed, with planning permission and not dependent on the scheme
38 | 4 - Economic Appraisal | Tab 4.1 - Potential Dep Dev Sites | 26 | This site is in pre-construction according to Table 3.4. As above, is there planning permission, and how is it linked to the scheme? | Dependent development table updated - this development now considered committed, with planning permission and not dependent on the scheme
39 | 4 - Economic Appraisal | Tab 4.1 - Potential Dep Dev Sites | 26 | This site is listed as already under construction in table 3.4 – cannot be dependent unless there is a planning link | Dependent development table updated - this development is considered committed, with planning permission, however also dependent on the scheme - see updated dependency justrification column. The Waterside Employment Site (Parcel A) site conttibuted land directly to the current proposed scheme in the form of an S106 contribution
40 | 4 - Economic Appraisal | Tab 4.1 - Potential Dep Dev Sites | 26 | This site is listed as already under construction in table 3.3 – cannot have dependency unless there is a planning link – why is this proportion of the site dependent? (A S106 condition?) | Dependent development table updated - this development now considered committed, with planning permission and not dependent on the scheme
41 | 4 - Economic Appraisal | Tab 4.2 - Planning Gain Caluclations | 27 | This needs to follow latest WebTAG A2.2 and MHCLG guidance for calculation of Land Value Uplift. Importantly, the costs associated with the development of the site (construction, finance, fees) should be deducted from Gross Development Value to determine Residual Land Value, and then Existing Land Use Value subtracted to calculate the Land Value Uplift.Benchmark values from either BRICS, MHCLG databook or feasibility studies conducted for Blackburn with Darwen’s local plan development can be used to determine these. Recommend contacting MHCLG for advice on a proportionate approach to getting this information.Remember that House Price Growth and deflation/discounting need to be considered, particularly where sites are being accelerated by the scheme. | Land Value Uplift Calculations (now table 4.3) updated to reflect this methodology.
42 | 4 - Economic Appraisal | Tab 4.2 - Planning Gain Caluclations | 27 | Gross Site Area – the existing land value should be applied to gross site area as all the land, including open space, is taken out of current agricultural use | Value changed in Table to Gross Site Area
43 | 4 - Economic Appraisal | Tab 4.2 - Planning Gain Caluclations | 27 | Some of these sites may be entirely or partly brownfield, so brownfield land values will also be needed | Row for Browlfield Land price added into table
44 | 4 - Economic Appraisal | Tab 4.2 - Planning Gain Caluclations | 27 | How will additionality be determined? What is the approach to determining displacement? | In the context of project timescales, the complexity of additionality analysis, the avalibility of information required for analysis, the relative scope of the proposed scheme and the expected extent of its impacts, an assessment of displacement, as well as other additionalities, is likely to be beyond what we can achieve within the timescales available for completion of the business case and could be argued to be disproportionate to the scale of the project as a minor scheme package.
45 | 4 - Economic Appraisal | Tab 4.2 - Planning Gain Caluclations | 27 | You will need to include land value growth, deflation and discounting to a consistent base year (2010 prices and values for consistency with Transport Economic Efficiency) | land value growth, deflation and discounting to a consistent base year will be completed during economic appraisal/ caluculation of scheme BCR
46 | 4 - Economic Appraisal | 4.2 Proposed Methodology | 28 | Have you started Step 1 yet? If yes, can the screening proforma be provided. If no, can it be provided to us at the earliest opportunity. | DI screening proforma will be completed and prodvided as an appendicies to the social and distriutional impacts apprasial report and the main business case document
47 | 5 - Environment | 5.4 Proposed Methodology | 30 | Please can this table be provided | Table added to ASR Summarising the proposed environmemtal methodology for each scheme impact